## 🐛 Bug Tracker Sign in
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments | Parent items
BUG_001 | TC_005 | Logout |  | Logout from Head International School dashbord | S2 - Major | P1 - High | Functional | 1. Sign in with valid email and password. 2. Open the User Profile. 3. Click the Logout button | User should be logged out successfully and redirected to the Sign in page. | The user is redirected to the "Head International School" template. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 3.53.52 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10 | [10 empty] | No
BUG_002 | TC_010 | Sign in | Create Website | Check institution type page UI | S3 - Minor | P3 - Low | UI/UX | 1. Open Create Website page 2. Check Back to the Sign in button | The UI should display a back button for user navigation. | The back button is not present in the UI. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_004 | TC_024 | Create Website | College | Send verification email for College | S1 - Critical | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_005 | TC_031 | Create Website | University | Send verification email for University | S1 - Critical | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_006 | TC_038 | Create Website | Coaching Center | Send verification email for Coaching Center | S1 - Critical | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_007 | TC_045 | Create Website | Training Institute | Send verification email for Training Institute | S1 - Critical | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_008 | TC_052 | Create Website | Other | Send verification email for Other | S1 - Critical | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png | Screen Recording 2026-06-10 at 4.01.33 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_002 | TC_017 | Create Website | School | Send verification email for School | S2 - Major | P1 - High | Functional | 1. Open Verify Your Email step 2. Click Send Verification Code | System should send verification code to the email and allow user to continue website creation. | System failed to send email. Error shown: 'Failed to send email: (535, b'5.7.8 Error: authentication failed: (reason unavailable)')'. Next remained disabled, so website creation could not be completed. | QA | N/A | Brave Browser/Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-18 | Khonndokar Ahamed Alfa Sunny | 2026-06-18 | [12 empty] | BUG_002

## 🐛 Bug Tracker Dashboard and Aca
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments | Parent items
BUG_001 | TC_03 | Dashboard Overview |  | Verify notification button action | S2 - Major | P1 - High | Functional | 1. Open dashboard page 2. Click the notification button 3. Observe whether notification panel or notification page opens | Clicking the notification button should open notification list, dropdown, or notification page. | Notification button does not open anything after clicking. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 4.06.41 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_002 | TC_07 | Dashboard Overview | Notice Board | Verify Back button availability | S3 - Moderate | P2 - Medium | UI/UX, Usability | 1. Open Notice Board page 2. Check whether a Back button is available 3. Try to return to previous page using the page control | A clear Back button should be available so user can return to the previous page easily. | No clear Back button is available on the Notice Board page. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-10 at 4.08.23 PM.png | Screen Recording 2026-06-10 at 4.08.01 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_003 | TC_25 | Dashboard Overview | Admission Management | Verify Back button availability | S3 - Moderate | P2 - Medium | UI/UX, Usability | 1. Open Admission Management page 2. Check whether a Back button is available 3. Try to return to previous page using the page control | A clear Back button should be available so user can return to the previous page easily. | No clear Back button is available on the Admission Management page. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_004 | TC_44 | Dashboard Overview | Blog Management | Create new blog post with all required information | S2 - Major | P1 - High | Functional | 1. Click Create New Post. 2. Enter valid title, slug, content, publish setting, author, category, image and SEO details. 3. Click Save Post. 4. Check whether the post is created and appears in the blog list. | Blog post should be created successfully. User should see a success message and the new post should appear in the blog list. | Blog post was not created successfully from the create page. The system stayed on create form and showed a failed save message. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-10 at 4.17.49 PM.png,Screenshot 2026-06-10 at 4.17.54 PM.png,Screenshot 2026-06-10 at 4.17.58 PM.png,Screenshot 2026-06-10 at 4.18.03 PM.png | Bug-44.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_005 | TC_47 | Dashboard Overview | Activity Management | Create new activity with short content | S3 - Moderate | P2 - Medium | UI/UX, Validation | 1. Click New Activity 2. Enter activity title and required information 3. Enter short content less than 10 characters 4. Click Save Activity | System should stop saving and show a simple message like 'Content must be at least 10 characters long'. | System stopped saving, but the error message showed raw technical format instead of a clean user-friendly message. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Bug47.png |  | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_006 | TC_50 | Dashboard Overview | User Management | Create new user with required information | S2 - Major | P1 - High | UI/UX, Functional | 1. Click Add User 2. Fill first name, last name, username, email, phone, password and confirm password 3. Select role and status 4. Click Create User | New user should be created successfully after all required fields are filled. | Create user form opened, but role selection did not clearly show available role options, so user creation could not be completed properly. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Bug50.png |  | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_007 | TC_56 | Academic Calendar |  | Download academic calendar | S2 - Major | P1 - High | Functional | 1. Open Academic Calendar page 2. Click the download icon button | Calendar file should be downloaded or export should start. | Download icon button does not work; no file is downloaded and no action happens. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 4.30.01 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-10-06 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_008 | TC_56 | Academic Calendar |  | View, Edit, and Delete options are unavailable for events in Grid view | S2 - Major | P1 - High | Functional | 1. Sign in with valid credentials. 2. Open Academic Calendar. 3. Add an event with valid information. 4. Select Grid view. 5. Select the added event. | Users should be able to View, Edit, or Delete an added event directly from Grid view. | The event appears in Grid view, but no View, Edit, or Delete action is available. The actions appear only after switching to List view. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png,Screenshot 2026-06-17 at 11.37.40 AM.png,Screenshot 2026-06-17 at 11.34.09 AM 1.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_009 | TC_57 | Academic Calendar |  | Calendar action controls have a broken and inconsistent layout on mobile devices | S4 -Minor | P2 - Medium | UI/UX | 1. Sign in from a mobile device. 2. Open Academic Calendar. 3. Observe the Grid/List selector, Settings button, and Add Event button. | All action controls should follow a responsive layout with consistent alignment, spacing, dimensions, and readable text on mobile screens. | The Grid/List selector is displayed as a tall stacked block, the Settings button is visually separated, and the Add Event button is oversized with its text wrapping into multiple lines. The controls do not appear balanced or consistently aligned. | QA | N/A | Chrome / Vivo IQOO Z7 5g | Android 13 | WhatsApp Image 2026-06-17 at 11.05.12.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_010 | TC_58 | Admission Management |  | Delete action is unavailable for admission applications in Grid view | S2 - Major | P2 - Medium | Functional, UI/UX | 1. Sign in with valid credentials. 2. Open Admission Management. 3. Select Grid view. 4. Locate an application card. 5. Check the available actions. 6. Switch to List view and compare the actions. | Users should be able to View and Delete applications from both Grid and List views. | Grid view provides only the View Application option, while List view provides both View and Delete actions. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-17 at 4.13.45 PM.png,Screenshot 2026-06-17 at 4.13.52 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Media Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_005 | Media Management |  | List view is not available | S3 - Moderate | P2 - Medium | Functional | 1. Login as admin 2. Open Media Management 3. Click list view icon | Media files should be displayed in list/table view with file details and action buttons. | The page shows 'List View coming soon' instead of a working list view. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-14 | Khonndokar Ahamed Alfa Sunny | 2026-06-11

## 🐛 Bug Tracker Career & hero sec
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_005 | Career Management |  | Verify required field validation on new job circular form | S3 - Moderate | P2 - Medium | Functional, Validation | 1. Open Career Management. 2. Click Post New Job. 3. Keep required fields blank. 4. Click Save or Submit. | Clear validation messages should be shown near the required fields. | A raw error message is shown instead of clear field validation messages. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 4.58.14 PM.mov | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10

## 🐛 Bug Tracker Video Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_009 | Video Management |  | Delete button is missing for video item | S3 - Moderate | P2 - Medium | Functional | 1. Open Video Management page 2. Check an existing video card 3. Try to find a clear delete button for removing the video | A clear delete button should be available for deleting a video item. | Delete button is not available or not clearly shown for the video item. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-14 | Khonndokar Ahamed Alfa Sunny | 2026-06-11
BUG_002 | TC_016 | Video Management |  | Edit action is missing and Delete icon is barely visible on mobile | S2 - Major | P2 - Medium | UI/UX | 1. Sign in with valid credentials. 2. Open Video Management on a mobile device. 3. Locate an existing video card. 4. Observe the available action controls. | Both Edit and Delete actions should be clearly visible, properly positioned, and easy to identify from mobile devices. | No Edit action is visible on the video card. The Delete icon is displayed with very low contrast against the background, making it difficult to notice and use. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-17 at 15.22.39.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Hero Section Mana
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_004 | Hero Section Manager |  | Verify frontend page opens from hero section module | S2 - Major | P1 - High | Functional | 1. Open Hero Section Manager. 2. Click the Frontend Preview: Lake/view more option. 3. Check the opened frontend page. | Frontend page should open and show the school website hero section. | Frontend page shows Page Not Found. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 5.05.30 PM.mov | Open |  |  |  |  | Khonndokar Ahamed Alfa Sunny | 2026-06-10

## 🐛 Bug Tracker Promotion Managem
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_005 | Promotion Management |  | Live Now summary count does not match published promotion list | Medium | P2 - Medium | Functional, Data | 1. Open Promotion Management page 2. Check Live Now summary card 3. Compare the count with visible published promotion cards | Live Now count should show the correct number of active published promotions. | Live Now count shows 0 while a published promotion card is visible. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-14 | Khonndokar Ahamed Alfa Sunny | 2026-06-11
BUG_002 | TC_020 | Result Published Management |  | Participants table header text is unclear | Low | P3 - Low | UI/UX | 1. Open Exam Results page 2. Check table header labels | Column label should be clear and grammatically correct, such as Participants. | Column label shows 'Participate'. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  | The column header is displayed as "Participate", which is a verb. The header should use a noun such as "Participants" to accurately describe the column contents. |  | Mohammed Samir | 2026-06-14 | Khonndokar Ahamed Alfa Sunny | 2026-06-11
BUG_003 | TC_021 | Promotion Management |  | Archived empty state message is misleading | Low | P3 - Low | UI/UX | 1. Open Promotion Management page 2. Click Archived filter 3. Read the empty state message | The empty state should clearly say no archived promotions were found. | The message says no promotions found and suggests creating the first promotion, although promotions exist in other filters. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-14 | Khonndokar Ahamed Alfa Sunny | 2026-06-11
BUG_004 | TC_022 | Result Management |  | Result action buttons have an inconsistent and unbalanced mobile layout | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in with valid credentials. 2. Open Result Management on a mobile device. 3. Observe the School Result, Public Result, and Admission Result buttons. | All result action buttons should follow a consistent responsive layout with balanced dimensions, spacing, alignment, and readable labels. | School Result and Public Result are displayed as narrow side-by-side buttons with wrapped labels, while Admission Result is displayed as a full-width button below them. The inconsistent sizing and arrangement make the section look unbalanced. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_005 | TC_023 | Promotion Management |  | Promotion List view is not responsive on mobile devices | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in with valid credentials. 2. Open Promotion Management on a mobile device. 3. Select List view. 4. Observe the promotion table and row content. | The promotion List view should adapt to the mobile screen and keep all information readable, aligned, and accessible without clipping or excessive wrapping. | The table is compressed into the mobile viewport. Column headers and row values wrap into multiple lines, the layout appears crowded, and content on the right side is partially clipped. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-17 at 14.52.56.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Contact Managemen
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_002 | Contact Management |  | Filter messages by status | S2 - Major | P1 - High | Functional | 1. Open Contact Management. 2. Click the All Status dropdown. 3. Select any available status option. | Status dropdown should open and allow filtering messages by selected status. | Status dropdown button does not work. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | bug1.mov | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_002 | TC_003 | Contact Management |  | Open inbox message details | S3 - Moderate | P2 - Medium | Performance | 1. Open Contact Management. 2. Click any message from the inbox list. 3. Check how long the message details take to open. | Message details should open quickly after clicking the message. | Message details open very slowly. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-10 at 4.34.08 PM.mov | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_003 | TC_004 | Contact Management |  | Check contact add and edit options | S3 - Moderate | P2 - Medium | Functional, UI/UX | 1. Open Contact Management. 2. Check the page actions. 3. Look for Add and Edit options. | User should have clear Add and Edit buttons if contact records need to be managed. | Add and Edit buttons are not available. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-10 at 4.40.22 PM.png |  | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_004 | TC_005 | Contact Management |  | Check action button placement | S4 - Minor | P3 - Low | UI/UX, Usability | 1. Open Contact Management. 2. Select any inbox message. 3. Check Archive, Delete, and Mark as Replied button placement. | Action buttons should be clearly placed and easy to understand. | Archive is placed with Delete, and Mark as Replied is placed too low. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_005 | TC_006 | Contact Management |  | Check page performance during button actions | S2 - Major | P1 - High | Performance | 1. Open Contact Management. 2. Click Archive, Delete, or Mark as Replied. 3. Observe the response time. | Button actions should respond quickly without delay. | Button actions respond slowly and page performance is poor. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Bug5.mov | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_006 | TC_007 | Contact Management |  | Verify add and edit contact options | S3 - Moderate | P2 - Medium | Functional, UI/UX | 1. Open Contact Management. 2. Check list page actions. 3. Try to add a new contact. 4. Try to edit an existing contact. | Add and Edit buttons should be available if contact records are managed from this page. | No Add or Edit button is available. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10
BUG_007 | TC_008 | Contact Management |  | Verify action button placement and UI structure | S4 - Minor | P3 - Low | UI/UX, Usability | 1. Open Contact Management. 2. Check Archive, Delete and Mark as Replied button positions. 3. Review action button alignment. | Action buttons should be clearly separated and placed in a user-friendly layout. | Archive button is close to Delete button and Mark as Replied button is placed at the bottom. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 10/06/2026 | Khonndokar Ahamed Alfa Sunny | 2026-06-10

## 🐛 Bug Tracker Event Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_EM_001 | TC_010 | Event Management |  | Categories and Create Event buttons are excessively large on mobile | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in with valid credentials. 2. Open Event Management on a mobile device. 3. Observe the Categories and Create Event buttons. | The buttons should use a responsive size with proper alignment, spacing, and single-line readable labels where possible. | The buttons are oversized and occupy excessive screen space. The Create Event label wraps into two lines, making the mobile layout visually unbalanced. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-17 at 14.09.06.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_EM_002 | TC_011 | Event Management |  | Horizontal scrolling is unavailable in mobile List view | S2 - Major | P1 - High | Functional, Responsive | 1. Sign in with valid credentials. 2. Open Event Management on a mobile device. 3. Select List view. 4. Swipe horizontally across the event table. | Users should be able to scroll horizontally and access every event column and action in List view. | The event table does not scroll horizontally. Columns on the right side are clipped, preventing users from viewing complete event information and actions. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-17 at 14.11.13.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker FAQ & Gallery Man
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_GM_001 | TC_011 | Gallery Management |  | Delete option is unavailable for images in List view | S2 - Major | P2 - Medium | Functional | 1. Sign in with valid credentials. 2. Open Gallery Management. 3. Select List view. 4. Locate an existing image. 5. Check the available action buttons. | Users should be able to delete an image directly from List view using a visible Delete option. | The List view displays only an Edit button for each image. No Delete button or delete action is available. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-17 at 2.47.00 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_FAQ_001 | TC_012 | FAQ Management |  | Grid view option is unavailable in FAQ Managemen | S3 - Minor | P3 - Low | UI/UX | 1. Sign in with valid credentials.2. Open FAQ Managem | Users should be able to switch between Grid and L | FAQ Management displays only the table/list layout, and | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-17 at 2.48.14 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Organization
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_021 | organization | Leadership Messages | Empty required values can be saved | High | P1 - High | Functional, Validation | 1. Open Leadership Messages 2. Click Add/Edit 3. Keep required fields empty 4. Click Save | System should show required field validation and should not save empty values. | System saves empty values without required validation. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_002 | TC_027 | organization | Staff Management | Staff section counts change incorrectly | Medium | P2 - Medium | Functional, Data | 1. Open Staff Management 2. Note All, Marketing, and Active counts 3. Select Inactive, On Leave, or Retired section 4. Check the counts again | Counts should remain accurate for All, Marketing, and Active sections. | All 1 becomes All 0, Marketing 1 becomes Marketing 0, Active 1 becomes Active 0. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png,image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker User Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_015 | User Management | User Management | User name and username are almost invisible in user details | Minor | P2 - Medium | UI/UX | 1. Open User Management. 2. Open a user's details. 3. Check the user name and username at the top of the details window. | The user name and username should have enough contrast and be clearly readable. | The user name and username appear in a very light color and are almost invisible on the light background. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Form Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_FM_001 | TC_FM_001 | Form Management |  | Form input fields do not accept or retain user input | S1 - Critical | P1 - High | Functional | 1. Sign in with valid credentials. 2. Open Form Management. 3. Open or create a form. 4. Select any input field. 5. Enter valid data. | All form input fields should accept and retain valid user input. | None of the input fields accept or retain entered values, preventing form configuration and data entry. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 4.45.48 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_FM_002 | TC_FM_002 | Form Management |  | Edit functionality does not work for existing forms | S2 - Major | P1 - High | Functional | 1. Sign in with valid credentials. 2. Open Form Management. 3. Locate an existing form. 4. Click Edit. 5. Attempt to modify and save the form. | The form should open in edit mode, allow modifications, and save the updated information. | The Edit function does not work, so existing forms cannot be modified. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 4.48.37 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_FM_003 | TC_FM_003 | Form Management |  | Copy button does not copy form URL or embed code | S2 - Major | P2 - Medium | Functional | 1. Sign in with valid credentials. 2. Open Form Management. 3. Open the sharing or publishing section. 4. Click Copy beside the public URL or embed code. 5. Attempt to paste the copied content. | The selected URL or embed code should be copied successfully to the clipboard. | The Copy button does not perform any action, and no content is copied. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 4.48.37 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_FM_004 | TC_FM_004 | Form Management |  | Share button is unresponsive for existing forms | S2 - Major | P2 - Medium | Functional | 1. Sign in with valid credentials. 2. Open Form Management. 3. Open an existing form. 4. Click Share. | The Share button should display sharing options or generate a valid shareable link. | The Share button does not respond, and no sharing options are displayed. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 4.48.37 PM.png |  | Open |  |  |  |  | Mohammed samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21

## 🐛 Bug Tracker Templates
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_TM_001 | TC_TM_002,TC_TM_003 | Template Management |  | Eye icon and Preview button do not open template preview | S2 - Major | P1 - High | Functional | 1. Open Settings > Template Management. 2. Locate an available template. 3. Click the eye icon or Preview button. | The selected template should open in preview mode and display the complete design. | Neither the eye icon nor the Preview button opens a preview or produces a visible response. |  | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 3.46.58 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-18 | Khonndokar Ahamed Alfa Sunny | 2026-06-18
BUG_TM_002 | TC_TM_004 | Template Management |  | Request a Custom Design button is unresponsive | S2 - Major | P2 - Medium | Functional | 1. Open Settings > Template Management. 2. Scroll to the custom design request section. 3. Click Request a Custom Design. | The button should open a request form, modal, or contact workflow. | The button is unresponsive and no request process opens. |  | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 3.41.07 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-18 | Khonndokar Ahamed Alfa Sunny | 2026-06-18

## 🐛 Bug Tracker Page Customizatio
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_PC_001 | TC_PC_006 | Page Customization |  | Body Content section placement causes excessive scrolling | S3 - Minor | P2 - Medium | UI/UX | 1. Open Page Customization. 2. Click Create New Page. 3. Add multiple fields. 4. Observe the Body Content section position. | Body Content should remain above the dynamic field area, with new fields appearing below it. | Body Content is placed below dynamic sections and moves further down as fields are added, causing unnecessary scrolling. |  |  | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-21 at 2.23.07 PM.png,Screenshot 2026-06-21 at 2.22.49 PM.png,Screenshot 2026-06-21 at 2.22.58 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_002 | TC_PC_007 | Page Customization |  | Dynamically added fields can be saved without values | S2 - Major | P2 - Medium | Validation | 1. Open Create New Page. 2. Enter valid Page Title and URL Slug. 3. Add a field and leave it empty. 4. Save the page. | Added fields should be validated or unused empty fields should be removed before saving. | The page saves successfully even though intentionally added fields contain no value. |  |  | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-21 at 2.21.43 PM.png,Screenshot 2026-06-21 at 2.21.28 PM.png,Screenshot 2026-06-21 at 2.21.35 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_003 | TC_PC_009 | Page Customization |  | Preview of a newly created page displays Page Not Found | S2 - Major | P1 - High | Functional | 1. Create and save a valid page. 2. Return to Page Customization. 3. Click the page preview/view action. | The selected page should open on the frontend and display its saved content. | The frontend displays Page Not Found instead of the created page. |  |  | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-21 at 2.15.21 PM.png,image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_004 | TC_PC_011 | Page Customization |  | Blurry partial image appears above Create New Page section | S3 - Minor | P2 - Medium | UI/UX | 1. Open Page Customization. 2. Observe the upper section above Create New Page. | The upper image/banner should render clearly and completely. | A blurry half-rendered image is displayed in the upper section. |  |  | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-18 at 3.19.10 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_005 | TC_PC_012 | Page Customization |  | Create New Page button is oversized on mobile | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in on a mobile device. 2. Open Page Customization. 3. Observe the Create New Page button. | The button should be responsively sized, properly aligned, and display a clear label without excessive wrapping. | The button is too large for the mobile layout, and its label wraps into multiple lines, creating an unbalanced header. | Mobile Browser |  | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-18 at 16.15.43.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_006 | TC_PC_013 | Page Customization |  | Body Content titles and controls overflow outside their cor | S2 - Major | P1 - High | UI/UX | 1. Sign in on a mobile device. 2. Open a Page Customization editor. 3. Scroll to Body Content. 4. Observe the added Rich Text or Image block. | All content-block titles and controls should fit inside their cards and remain fully visible within the mobile viewport. | Content-block titles and editor controls extend outside their cards and are partially clipped beyond the right side of the screen. | Mobile Browser |  | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-18 at 16.15.44.jpeg,aaaa.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21
BUG_PC_007 | TC_PC_014 | Page Customization |  | Add Field button becomes blank after adding a new field o | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in on a mobile device. 2. Open the Page Customization editor. 3. Add a new field. 4. Observe the Add Field buttons. | Each Add Field button should continue displaying its icon and label after a field is added. | One Add Field button changes into a blank white button with no visible icon or label. | Mobile Browser |  | Chrome / Vivo IQOO z7 5g | Android 15 | WhatsApp Image 2026-06-18 at 16.15.44.jpeg |  | Open |  |  |  |  | Mohammed Samir | 2026-06-21 | Khonndokar Ahamed Alfa Sunny | 2026-06-21

## 🐛 Bug Tracker Menu Management
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_MM_001 | TC_MM_005 | Customization | Menu Management | Tablet preview content is partially cropped | S3 - Minor | P2 - Medium | UI/UX | 1. Sign in with valid credentials. 2. Open Customization > Menu Management. 3. Click the tablet preview icon. 4. Observe the preview frame and content. | The tablet preview should fit the selected layout properly and show important content without cropping. | The tablet preview content is partially cropped and does not fit Brave Browser cleanly inside the visible preview frame. | Brave Browser | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open
BUG_MM_002 | TC_MM_006,TC_MM_007 | Customization | Menu Management | Mobile preview frame has alignment and spacing issue | S3 - Minor | P2 - Medium | UI/UX | 1. Open Menu Management. 2. Select mobile preview mode. 3. Observe the preview frame and surrounding blank area. | The mobile preview should be centered in a clean mobile-width frame with consistent spacing. | The mobile preview frame leaves large blank side space and appears inconsistently aligned within the preview area. | Brave Browser | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open
BUG_MM_003 | TC_MM_008 | Customization | Menu Management | Preview section title/content is clipped at frame boundary | S3 - Minor | P2 - Medium | UI/UX | 1. Open Menu Management. 2. Scroll the website preview. 3. Observe section content near the bottom of the preview frame. | All section titles and page content should remain fully visible inside the preview frame. | A section title is partially visible/cut off at the bottom edge of the preview frame. | Brave Browser | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-25 at 11.14.39 AM.png,Screenshot 2026-06-25 at 11.14.27 AM.png |  | Open
BUG_MM_004 | TC_MM_010 | Customization | Menu Management | Footer contact information is cut off in preview | S2 - Major | P2 - Medium | UI/UX | 1. Open Menu Management. 2. Scroll the preview to the footer section. 3. Observe the Contact information area. | The full address, phone, and email should be visible inside the preview area. | The Contact section is clipped on the right side, and the email/contact text is not fully visible. | Brave Browser | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open
BUG_MM_005 | TC_MM_011 | Customization | Menu Management | Navigation Links list is difficult to scroll on mobile | S2 - Major | P1 - High | UI/UX | 1. Sign in on a mobile device. 2. Open Customization > Menu Management. 3. Scroll down through the Navigation Links list. 4. Try to reach lower menu items such as Blog, Event, Contact, or Zerin Space. | Users should be able to scroll smoothly and reach all navigation items on mobile without interaction difficulty. | The Navigation Links list is difficult to scroll on mobile, making it hard to reach lower menu items. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 |  | WhatsApp Video 2026-06-25 at 11.20.35.mp4 | Open
BUG_MM_006 | TC_MM_012 | Customization | Menu Management | Template preview is not visible on mobile device | S2 - Major | P1 - High | UI/UX | 1. Sign in on a mobile device. 2. Open Customization > Menu Management. 3. Observe the mobile layout. 4. Try to view the template preview area on the right side. | The template preview should be visible or accessible on mobile through a responsive layout, preview tab, toggle, or proper horizontal navigation. | The mobile screen shows only the Navigation Links panel, and the template preview on the right side is not visible or usable. | Mobile Browser | N/A | Chrome / Vivo IQOO z7 5g | Android 15 | image.png |  | Open

## 🐛 Bug Tracker General Settings
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_006 | Settings | General settings | Return is not updated after successful save | Major | P2 - Medium | Functional, Configuration | 1. Open General settings. 2. Update a value from inputs. 3. Click the apply button. 4. Reload the site and check the updated value. | The selected changes should be saved and clearly applied to the website. | A success message is displayed. The Return is not clearly reflected. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-17 at 4.44.36 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_002 | TC_010 | Settings | General settings | Social Share image cannot be removed | Major | P2 - Medium | Functional | 1. Block Life applies Moble. 2. Save the updates. 3. Go to the website's Social Share image. 4. Delete the selected image. 5. Save the settings. | The social Share images should be removed successfully. | The social Share image cannot be removed. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-17 at 4.39.16 PM.png,Screenshot 2026-06-17 at 4.39.25 PM.png,Screenshot 2026-06-17 at 4.39.42 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_003 | TC_014 | Settings | General settings | Availability and Coming soon dates show labels but are not applied | Major | P1 - High | Functional | 1. Navigate to Settings. 2. Select Publishance or Coming soon. 3. Save that the source message appears. 4. Open General settings. 5. Update the values of availability and availability. 6. Open Coming soon. 7. Check the source message. 8. Check the errors. 9. Check the save the website and verify the applied labels. | The selected dates should be saved and applied. Coming soon should display a coming soon page. | The message "Settings and local units updated is not applied. The website remains live. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-17 at 4.42.28 PM.png,Screenshot 2026-06-17 at 4.41.17 PM.png,Screenshot 2026-06-17 at 4.40.55 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_003 | TC_015 | Settings | General settings | Apply Coming soon into website | Major | P1 - High | Functional | 1. confirm that the source message appears. 2. Open General settings. 3. Update the values of availability and availability. 4. Open Coming soon. 5. Check the source message. 6. Check the errors. 7. Check the save the website and verify the applied labels. | The system should use Coming soon status, show a blocking message and display the coming soon labels on the website. | The system shows "Settings and local units updated The social Share image cannot be removed is not applied. The website remains live. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 |  | Screen Recording 2026-06-17 at 4.44.36 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-06-17 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Profile
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_006 | Settings | Profile Management | Large empty space appears at the top of the profile page | Minor | P2 - Medium | UI/UX | 1. Open the admin panel. 2. Select Profile. 3. Check the top section of the page. | The page should have balanced spacing and display a clear heading, label, or instruction at the top. | The top section contains a large empty space with no heading, label, or instruction, making the layout look incomplete. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-15 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Security & Access
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_003 | Settings | Security Management | Password change does not work | Major | P1 - High | Functional, Validation, Security | 1. Open Security. 2. Click Change Password. 3. Enter the current password. 4. Enter a valid new password. 5. Enter the same value in Confirm New Password. 6. Click Update Password. | The password should be updated successfully and a confirmation message should be displayed. | The password is not updated. The system displays "User data not found. Please re-login." | Security Test | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-15 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_002 | TC_004 | Settings | Security Management | Password fields do not have a show or hide option | Minor | P1 - High | UI/UX, Validation, Security | 1. Open Security. 2. Click Change Password. 3. Enter values in the password fields. 4. Check for a password visibility control. | Each password field should have a show or hide control so the user can verify the entered password. | No password visibility option is available for Current Password, New Password, or Confirm New Password. | Security Test | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-15 | Khonndokar Ahamed Alfa Sunny | 2026-06-17
BUG_003 | TC_006 | Settings | Security Management | Current active login session is not identified | Major | P1 - High | Usability, Security, Functional | 1. Open Security. 2. Scroll to Active Login Sessions. 3. Review the listed devices. 4. Check whether the current device is marked. | The currently logged-in device should be clearly marked as the current session. | The list shows device and browser details, but there is no indication of which device is the current active session. | Security Test | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-15 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Appearance & Them
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_001 | TC_006 | Settings | Theme Management | Text becomes transparent or difficult to read in Cosmic theme | Major | P1 - High | UI/UX | 1. Open Theme Change. 2. Apply the Cosmic theme. 3. Open different management pages. 4. Open the user profile or profile menu. 5. Check labels, menu items, headings, and profile text. | All text should use suitable dark-mode colors with enough contrast and remain clearly readable. | Many labels and letters appear transparent or use very low-contrast colors. Text is difficult to read across several management pages and in the user profile. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 | Screenshot 2026-06-15 at 4.13.34 PM.png,Screenshot 2026-06-15 at 4.13.04 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-15 | Khonndokar Ahamed Alfa Sunny | 2026-06-17

## 🐛 Bug Tracker Home Page
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_HP_001 | TC_HP_003 | Home Page |  | Header logo size and placement are not suitable | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Observe the institution logo in the header area. | Logo should be properly sized and aligned with the header design. | Logo appears small compared with the header area and does not look balanced with the placement. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 4.13.46 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_002 | TC_HP_004 | Home Page |  | Update and Holiday controls are unclear | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Observe Update and Holiday controls. | Controls should clearly indicate whether they are buttons, tabs, or labels. | Update appears like a button while Holiday appears like plain text, making the purpose unclear. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 4.13.46 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_003 | TC_HP_005 | Home Page |  | Holiday control does not work clearly | S2 - Major | P1 - High | Functional | 1. Open the Home Page. 2. Click Holiday. | Holiday should open related content or show a clear active state if it is clickable. | Clicking Holiday does not show any clear action or active state. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 4.13.46 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_004 | TC_HP_006 | Home Page |  | Night mode creates readability issues | S2 - Major | P1 - High | UI/UX | 1. Open the Home Page. 2. Switch to night mode. 3. Review visible sections. | Night mode should keep all text and UI elements readable. | Several sections have low-contrast text and dark card readability issues. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 4.14.26 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_005 | TC_HP_007 | Home Page |  | Navigation text is hard to read in night mode | S3 - Minor | P2 - Medium | UI/UX | 1. Switch to night mode. 2. Observe navigation menu text and active Home state. | Navigation text should remain readable in right mode. | Some navigation text and active menu styling are difficult to read clearly. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_006 | TC_HP_012 | Home Page |  | Important Links card has no visible link content | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Observe the important Links card. | Important Links should show links or a clear empty-state message. | The Important Links card appears empty without useful content. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_007 | TC_HP_013 | Home Page |  | Authority card images are broken | S2 - Major | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Scroll to Message from Authority. | Authority cards should show valid images and message content. | Principal and Vice Principal images are broken/missing and placeholder message content is displayed. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_008 | TC_HP_014 | Home Page |  | Teachers section has excessive blank space | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Scroll to Teachers section. | Teacher cards should be displayed in a balanced layout. | Only one teacher card is visible and a large blank area remains. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_009 | TC_HP_016 | Home Page |  | Testimonial text has low contrast in night mode | S3 - Minor | P2 - Medium | UI/UX | 1. Switch to night mode. 2. Scroll to What People Say. | Testimonial content should remain readable. | Some testimonial text has low contrast against the dark card background. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_010 | TC_HP_017 | Home Page |  | Latest News & Activities section is empty | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Scroll to Latest News & Activities. | The section should show content or a clear empty-state message. | No content or clear empty-state message appears under the heading. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_011 | TC_HP_018 | Home Page |  | Latest Blog Posts metadata has low contrast in right mode | S3 - Minor | P2 - Medium | UI/UX | 1. Switch to night mode. 2. Scroll to Latest Blog Posts. | Metadata and action links should be readable. | Blog metadata and View More links are low-contrast and difficult to read. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_012 | TC_HP_019 | Home Page |  | Footer information appears incomplete | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Home Page. 2. Scroll to footer. | Footer should show valid institution information, links, and contact details. | Some footer areas appear incomplete, including missing/empty link information. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_013 | TC_HP_020 | Home Page |  | Floating phone button may cover page content | S3 - Minor | P3 - Low | UI/UX | 1. Open the Home Page. 2. Scroll through the page. 3. Observe the lower-right area. | Floating phone button should not cover important content or actions. | The floating phone button appears over the lower-right content area. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_014 | TC_HP_021 | Home Page |  | Main actions respond slowly | S2 - Major | P1 - High | Performance | 1. Open the Home Page. 2. Click major navigation/action buttons. 3. Observe response time. | Main actions should respond without noticeable delay. | Some main buttons/actions take approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_HP_015 | TC_HP_022 | Home Page |  | Night mode layout has large empty spacing | S3 - Minor | P3 - Low | UI/UX | 1. Switch to night mode. 2. Scroll from top to footer. | Sections should maintain balanced spacing. | Some sections show large empty dark space, making the layout feel unbalanced. | QA | N/A | Brave Browser / Macbook air m4 13 | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker About Us
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_AU_001 | TC_AU_003 | About Us | Institution Profile | About Institution Details button does not work | S2 - Major | P1 - High | Functional | 1. Open About Us > Institution card. 2. Locate the About Institution card. 3. Click the Details button. | The Details button should navigate to the full Institution Profile details page. | The Details button does not open the expected details page. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 11.57.03 AM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_002 | TC_AU_006 | About Us | Administrator | Administrators page shows empty content without helpful fallback | S3 - Minor | P2 - Medium | UI/UX | 1. Open the About Us dropdown. 2. Click Administrators. 3. Observe the content area. | The page should show administrator information or a clear helpful empty-state message. | Only 'No information found' is displayed with a large empty area and no useful instruction. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_003 | TC_AU_007 | About Us |  | Read More button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the About Us related home section. 2. Click Read More. 3. Observe response time. | The Read More button should respond quickly and navigate to the related page. | The Read More button response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_004 | TC_AU_008 | About Us | Administrator | Admission button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the About Us page. 2. Click Admission. 3. Observe response time. | The Admission button should respond quickly and open the admission page or workflow. | The Admission button response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_005 | TC_AU_009 | About Us |  | Login button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the About Us page. 2. Click Login. 3. Observe response time. | The Login button should respond quickly and open the login page. | The Login button response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_006 | TC_AU_010 | About Us |  | Language dropdown response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the About Us page. 2. Click the English language dropdown. 3. Observe response time. | The language dropdown should open quickly without lag. | The language dropdown response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_AU_007 | TC_AU_011 | About Us |  | Floating phone/contact button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the About Us page. 2. Click the floating phone/contact button. 3. Observe response time. | The floating phone/contact button should respond quickly and trigger the intended contact action. | The floating phone/contact button response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Staff
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_ST_001 | TC_ST_003 | Staff |  | Teachers page has excessive blank space and unbalanced layout | S3 - Minor | P2 - Medium | UI/UX | 1. Open Staff > Teachers. 2. Observe the teacher card and surrounding empty area. | Teacher cards should use balanced page spacing and align properly. | Only one teacher card appears on the left side, leaving a large blank area across the page. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_002 | TC_ST_005 | Staff |  | Teacher details modal is small and hard to read | S3 - Minor | P2 - Medium | UI/UX | 1. Open Staff > Teachers. 2. Click Details on the teacher card. 3. Observe the modal content and spacing. | The details modal should be comfortably readable with proper spacing and sufficient size. | The details modal appears small and the content looks cramped, reducing readability. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_003 | TC_ST_007 | Staff |  | Committee Members page is empty without empty-state message | S3 - Minor | P2 - Medium | UI/UX | 1. Open Staff dropdown. 2. Click Committee Members. 3. Observe the page content. | The page should display committee member cards or a clear empty-state message if no members are available. | The page displays only the Committee Members heading with a large empty area and no empty-state message. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_004 | TC_ST_009 | Staff |  | Staff dropdown response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the website. 2. Click the Staff menu. 3. Observe dropdown response time. | The Staff dropdown should open quickly without noticeable delay. | The Staff dropdown response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_005 | TC_ST_010 | Staff |  | Teachers menu navigation response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Staff dropdown. 2. Click Teachers. 3. Observe page loading response time. | The Teachers page should load quickly after clicking the menu option. | The Teachers page response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_006 | TC_ST_011 | Staff |  | Committee Members menu navigation response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Staff dropdown. 2. Click Committee Members. 3. Observe page loading response time. | The Committee Members page should load quickly after clicking the menu option. | The Committee Members page response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_ST_007 | TC_ST_012 | Staff |  | Teacher Details button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Staff > Teachers. 2. Click Details on the teacher card. 3. Observe modal opening response time. | The teacher details modal should open quickly without delay. | The teacher Details button response is delayed during testing. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Academics
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_AC_001 | TC_AC_004 | Academics |  | Academic Year 2026 value shakes on hover | S3 - Minor | P2 - Medium | UI/UX | 1. Open Academics > Public Examination. 2. Move the mouse cursor over the Academic Year dropdown value. 3. Observe the selected year text. | The selected Academic Year value should remain stable when hovered. | The 2026 value shakes/moves when the mouse cursor is placed over it. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  | Screen Recording 2026-06-24 at 12.33.48 PM.mov | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Notice
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_NO_001 | TC_NO_006 | Notice |  | Notice search behavior cannot be clearly confirmed | S3 - Minor | P2 - Medium | Functional | 1. Open Notice Board. 2. Enter a notice keyword in the search field. 3. Observe the notice list. | Search should filter the notice list based on entered keyword. | The search field is visible, but search behavior is not clearly confirmed from the available page state. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_002 | TC_NO_007 | Notice |  | Notice category filter behavior cannot be clearly confirmed | S3 - Minor | P2 - Medium | Functional | 1. Open Notice Board. 2. Select a notice category. 3. Observe the list result. | The category filter should update the notice list according to the selected category. | The filter is visible, but behavior is not clearly confirmed from the available page state. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_003 | TC_NO_008 | Notice |  | Notice Board page has excessive blank space | S3 - Minor | P3 - Low | UI/UX | 1. Open Notice Board. 2. Observe the notice list and page spacing. | The Notice Board should use balanced spacing around available notices. | A large unused blank area appears around the single notice item. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_004 | TC_NO_009 | Notice |  | Notice details page has unbalanced empty side area | S3 - Minor | P3 - Low | UI/UX | 1. Open a notice details page. 2. Observe the details area and side panel spacing. | The page should maintain balanced content spacing. | The page leaves a large blank area because only one side-panel notice is available. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_005 | TC_NO_010 | Notice |  | Notice menu response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the website. 2. Click Notice. 3. Observe response time. | The Notice page should open quickly. | The Notice menu action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_006 | TC_NO_011 | Notice |  | Notice item click response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Notice Board. 2. Click the Holiday notice. 3. Observe response time. | The notice details page should open quickly. | The notice item action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_NO_007 | TC_NO_012 | Notice |  | Notice search/filter response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Notice Board. 2. Use search and category filter. 3. Observe response time. | Search and filter actions should respond quickly. | Search/filter actions take approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Gallery
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_GA_001 | TC_GA_005 | Gallery |  | Photo preview modal has no clear close button | S2 - Major | P2 - Medium | UI/UX | 1. Open Gallery > Photos. 2. Click a photo thumbnail. 3. Observe modal controls. | A clearly visible close button should be available on the modal. | No clear close button is visible on the preview modal. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_002 | TC_GA_006 | Gallery |  | Photo preview modal has no next/previous controls | S3 - Minor | P2 - Medium | UI/UX | 1. Open a gallery photo preview. 2. Observe modal navigation controls. | Next and previous controls should be available for browsing images. | No clear next/previous controls are visible. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_003 | TC_GA_007 | Gallery |  | Floating contact button remains visible over photo preview | S3 - Minor | P2 - Medium | UI/UX | 1. Open Gallery > Photos. 2. Open a photo preview model. 3. Observe lower-right area. | Floating buttons should not overlay preview modals. | The floating contact button remains visible over the preview area. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_004 | TC_GA_008 | Gallery |  | Videos page is blank without useful empty-state message | S2 - Major | P1 - High | UI/UX | 1. Open Gallery dropdown. 2. Click Videos. 3. Observe the page content. | The page should show video content or a clear empty-state message. | The Videos page displays a blank content area. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_005 | TC_GA_010 | Gallery |  | Photos menu response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Gallery dropdown. 2. Click Photos. 3. Observe response time. | The Photos page should open quickly. | The Photos action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_006 | TC_GA_011 | Gallery |  | Videos menu response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Gallery dropdown. 2. Click Videos. 3. Observe response time. | The Videos page should open quickly. | The Videos action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_007 | TC_GA_012 | Gallery |  | Image preview response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Gallery > Photos. 2. Click a photo thumbnail. 3. Observe response time. | The preview modal should open quickly. | The image preview takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_GA_008 | TC_GA_013 | Gallery |  | Gallery page has excessive empty space | S3 - Minor | P3 - Low | UI/UX | 1. Open Gallery > Photos. 2. Observe gallery grid and page spacing. | Gallery content should use balanced layout spacing. | A large empty area remains after the available photo cards. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Blog and Event
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_BE_001 | TC_BE_003 | Blog |  | Blog listing has excessive blank space | S3 - Minor | P2 - Medium | UI/UX | 1. Open Blog page. 2. Observe the blog card grid and page spacing. | Blog cards should be arranged with balanced spacing and no excessive unused area. | Only two blog cards appear on the left side, leaving a large blank area. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_002 | TC_BE_005 | Event |  | Event menu opens Page Not Found | S1 - Critical | P1 - High | Functional | 1. Open the website. 2. Click Event from the header menu. | The Event page should open and show upcoming events or a clear empty state. | A Page Not Found page is displayed. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Zohayer Al Prova | 2026-06-25
BUG_BE_003 | TC_BE_007 | Blog |  | Upcoming Events card shows empty content | S3 - Minor | P2 - Medium | UI/UX | 1. Open a blog detail page. 2. Observe the Upcoming Events card. | The card should display event data or a more useful empty-state design. | The card only shows 'No events found' and leaves the area incomplete. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 2.51.12 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_004 | TC_BE_009 | Blog |  | Share options panel overlaps article content | S3 - Minor | P2 - Medium | UI/UX | 1. Open a blog detail page. 2. Click Share. 3. Observe the options panel. | Share options should appear without covering important article content. | The share options panel overlays part of the article content. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 2.54.05 PM.png,Screenshot 2026-06-24 at 2.54.11 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_005 | TC_BE_010 | Blog |  | Share dialog interrupts article reading flow | S3 - Minor | P3 - Low | UI/UX | 1. Open a blog detail page. 2. Click Share. 3. Select a share method. | The share dialog should be clear and should not confuse the user. | The share dialog opens over a dimmed page and interrupts normal article reading. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 2.57.18 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_006 | TC_BE_011 | Blog |  | Blog menu response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the website. 2. Click Blog. 3. Observe response time. | The Blog page should open quickly. | The Blog menu action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_007 | TC_BE_012 | Event |  | Event menu response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open the website. 2. Click Event. 3. Observe response time. | The Event page should open quickly. | The Event menu action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_008 | TC_BE_013 | Blog |  | See Details action response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open Blog page. 2. Click See Details. 3. Observe response time. | The detail page should open quickly. | The See Details action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_009 | TC_BE_014 | Blog |  | Share button response is delayed | S3 - Minor | P2 - Medium | Performance | 1. Open a blog detail page. 2. Click Share. 3. Observe response time. | Share options should open quickly. | The Share action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_BE_010 | TC_BE_015 | Blog |  | Blog detail page layout shifts while scrolling | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Blog page. 2. Click See Details on a blog card. 3. Scroll the Blog detail page up and down. 4. Observe the header, article card, and right-side area. | The page should scroll smoothly without layout shifting or unstable header/content positioning. | The Blog detail page layout shifts/jumps while scrolling and the content/header position appears unstable. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25

## 🐛 Bug Tracker Activity & Career
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_ACR_001 | TC_ACR_002 | Activity |  | Activity page has no content or empty-state message | S2 - Major | P2 - Medium | UI/UX | 1. Open the website. 2. Click Activity from the header menu. 3. Observe the content area below the Campus Activities heading. | The Activity page should display activity content or a clear empty-state message when no content is available. | Only the Campus Activities heading is displayed and the content area is blank. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 4.20.43 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-24 | Khonndokar Ahamed Alfa Sunny | 2026-06-24
BUG_ACR_002 | TC_ACR_014 | Careers |  | Careers listing section has no clear heading | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Careers page. 2. Scroll to the job listing/search area. 3. Observe the section title. | The Careers listing area should display a clear heading such as Current Openings or Available Positions. | No clear heading is displayed above the Careers listing/search area, so the section context is unclear. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-24 | Khonndokar Ahamed Alfa Sunny | 2026-06-24
BUG_ACR_003 | TC_ACR_015 | Careers |  | Faculty label is almost invisible beside Full-time badge | S3 - Minor | P2 - Medium | UI/UX | 1. Open the Careers page. 2. Observe the job card category labels. 3. Check the Faculty label beside the Full-time badge. | The Faculty label should be clearly visible and readable. | The Faculty label is almost invisible because the text color has very low contrast with the badge background. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 4.20.11 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-24 | Khonndokar Ahamed Alfa Sunny | 2026-06-24

## 🐛 Bug Tracker Contact
Bug ID | Test Case ID | Module / Feature | Sub-Module | Bug Title / Summary | Severity | Priority | Bug Type | Steps to Reproduce | Expected Behavior | Actual Behavior | Environment | Build / Version | Browser / Device | OS | Screenshot / Link | Video Evidence | Bug Status | Root Cause | Root Cause Category | Fix Description | Fix Commit / PR | Reported By | Date Reported | Assigned To | Date Assigned | Fixed By | Date Fixed | Verified By | Date Verified | Regression Risk | Duplicate Of | Related Bug IDs | Sprint / Release | Reopen Count | Last Reopen Date | SLA Breach | Notes / Comments
BUG_LT_001 | TC_LT_006 | Contact |  | Contact form does not clear after fixed validation failed for invalid inputs | S1-Minor | P2-Medium | Validation | 1. Open Contact forms. 2. Submit form without inputs. 3. Click Send Message. | Clear validation messages should be displayed besides each input field. | The form takes an unreasonable time to validate and does not clear the values or error message. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_002 | TC_LT_007 | Contact |  | Captcha challenge covers contact form fields | S3-Minor | P2-Medium | UI/UX | 1. Open Contact forms. 2. Click the captcha refresh. 3. Click refresh. 4. Observe the captcha challenge placement. | The captcha challenge should appear without blocking important web elements. | The captcha pops-up covers the contact fields and makes the input unresolvable. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_003 | TC_LT_009 | Contact |  | Contact form accumulates data unless addressed or a reset step displays | E3-Misc | P3-Low | UI/UX | 1. Submit form again with valid data. 2. Observe the success message and form data. | The success alert should clarify a specific calculation and provide useful next-step information. | A generic success message is shown and the empty form remains visible without a reference or next-step details. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_004 | TC_LT_010 | Contact |  | Call to action opens an external phone prompt and interrupts page flow | S5-Minor | P2-Medium | Functional | 1. Open Contact page. 2. Click floating contact button. 3. Click Call Us. | The system should provide a clear phone call action or display phone details without confusing interruption. | The browser shows an external phone application prompt over the page. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_005 | TC_LT_011 | Contact |  | FAQ answer displays placeholder hiding text | S2-Major | P2-Medium | content | 1. Open Contact page. 2. Expand the answer process start FAQ item. 3. Read the answer. | The FAQ should display meaningful user-facing information. | The FAQ answer displays 'Checking the FAQ, why' which appears to be placeholder testing text. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | image.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_006 | TC_LT_012 | Contact |  | Admissions application submission fails due to email authentication error | E5-Critical | P5-High | Functional | 1. Open Admission form. 2. Click Online Admission. 3. Fill admission related data. 4. Submit the application. | The application should be submitted successfully. | Submission fails and displays an email authentication failure message. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 2.49.18 PM.png,Screenshot 2026-06-22 at 2.49.42 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_007 | TC_LT_014 | Contact |  | Admission form response technical error email to user | S2-Major | P5-High | UI/UX | 1. Submit the Admission form. 2. Observe the failure message. | A clearer error message should be displayed without expecting technical error details. | The page displays one email authentication error details including SMTP code 550. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 2.49.42 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_008 | TC_LT_018 | Contact |  | Admission form fields are partially hidden while scrolling | S3-Minor | P2-Medium | UI/UX | 1. Open Online Admission form. 2. Scroll through the forms. 3. Observe the fields labels. | All fields and labels should remain visible and readable while scrolling. | Some upper fields and labels are partially hidden due to sticky header and scroll position. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-22 at 2.47.05 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_009 | TC_LT_019 | Contact |  | Contact form image area is oversized compared with form | S5-Minor | P3-Low | UI/UX | 1. Open Contact page. 2. Observe page layout. 3. Compare the form area with the image area beside it. | The form and image should have balanced visual weight. | The image beside the form occupies a very large area and creates an unbalanced layout. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 | Screenshot 2026-06-24 at 2.37.01 PM.png |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_010 | TC_LT_023 | Contact |  | Contact menu navigation response is delayed | S3-Minor | P2-Medium | Performance | 1. Open the website. 2. Hover over the the header menu. 3. Observe response time. | The Contact menu should open within an acceptable time without noticeable delays. | The Contact takes approximately 3-5 seconds to open or respond after clicking the menu. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_011 | TC_LT_024 | Contact |  | Online Admission button response is delayed | S3-Minor | P2-Medium | Performance | 1. Open Contact page. 2. Click Online Admission. 3. Observe response time. | The Online Admission page should open quickly after clicking the button. | The action takes approximately 3-5 seconds to open the next page. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_012 | TC_LT_025 | Contact |  | Send Message button response is delayed | S5-Minor | P2-Medium | Performance | 1. Fill the Contact form with valid data. 2. Complete captcha. 3. Click Send Message. 4. Observe response time. | The submission result should appear quickly after clicking Send Message. | The form takes approximately 3-5 seconds to show the result after clicking Send Message. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_013 | TC_LT_026 | Contact |  | FAQ expand/collapse response is delayed | S5-Minor | P2-Medium | Performance | 1. Open FAQ section. 2. Click the FAQ expand/collapse button. 3. Observe response time. | The FAQ item should expand or collapse immediately. | The FAQ action takes approximately 3-5 seconds to respond. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-25 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_014 | TC_LT_027 | Contact |  | Call Us button response is delayed | S5-Minor | P2-Medium | Performance | 1. Open floating contact menu. 2. Click Call Us. 3. Observe response time. | The Call Us action should respond quickly. | The action takes approximately 3-5 seconds to respond after clicking Call Us. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_015 | TC_LT_028 | Contact |  | Email Us button response is delayed | S5-Minor | P2-Medium | Performance | 1. Open floating contact menu. 2. Click Email Us. 3. Observe response time. | The Email Us action should respond quickly. | The action takes approximately 3-5 seconds to respond after clicking Email Us. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_016 | TC_LT_029 | Contact |  | Login button response is delayed from Contact page | S5-Minor | P2-Medium | Performance | 1. Open Contact page. 2. Click the Login button. 3. Observe response time. | The Login page should open quickly after clicking Login. | The action takes approximately 3-5 seconds to open or respond after clicking Login. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25
BUG_LT_017 | TC_LT_030 | Contact |  | Submit Application button response is delayed | S5-Minor | P2-Medium | Performance | 1. Open Online Admission. 2. Click Submit Application. 3. Click Submit Application. 4. Observe response time. | The Submit Application action should respond quickly. | The action takes approximately 3-5 seconds to respond after clicking Submit Application. | QA | N/A | Brave Browser / Macbook air m4 13 & Chrome / Vivo IQOO z7 5g | macOS 26.5.1 & Android 15 |  |  | Open |  |  |  |  | Mohammed Samir | 2026-06-22 | Khonndokar Ahamed Alfa Sunny | 2026-06-25